## Sheet1
Legend
|  |  |  | Dataset |  |  |  |  | Regularization |  |  |  |  | Feature Importance |  |  |  |  | Model Architecture |  |  |  |  | Submission
Stephanie A. Taraga |  |  |  | D |  |  |  |  | R |  |  |  |  | F |  |  |  |  | M |  |  |  |  | S
Project start date: 14 Jan 2025
|  |  |  | January | [18 empty] | February | [27 empty] | March | [30 empty] | April
Task Description | Category | Start | Days | time axis 2025-01-13 to 2025-04-07
Acquire and process data | D | 2025-01-13 | 5 | bar: 2025-01-13 to 2025-01-17
Train existing model with larger dataset | D | 2025-01-18 | 2 | bar: 2025-01-18 to 2025-01-19
Evaluate model performance | D | 2025-01-20 | 4 | bar: 2025-01-20 to 2025-01-23
Perform feature importance analysis and compare results with existing literature | F | 2025-01-20 | 4 | bar: 2025-01-20 to 2025-01-23
Research regularization techniques | R | 2025-01-24 | 5 | bar: 2025-01-24 to 2025-01-28
Apply promising regularization techiniques | R | 2025-01-26 | 10 | bar: 2025-01-26 to 2025-02-04
Evaluate model performance | R | 2025-02-03 | 4 | bar: 2025-02-03 to 2025-02-06
Perform feature importance analysis and compare results with existing literature | F | 2025-02-03 | 4 | bar: 2025-02-03 to 2025-02-06
Research model architectures | M | 2025-02-07 | 10 | bar: 2025-02-07 to 2025-02-16
Apply promising model architectures | M | 2025-02-13 | 15 | bar: 2025-02-12 to 2025-02-21; 2025-03-01 to 2025-03-05
READING WEEK | NA | 2025-02-22 | 7 | bar: 2025-02-22 to 2025-02-28
Evaluate model performance | M | 2025-03-06 | 7 | bar: 2025-03-06 to 2025-03-12
Perform feature importance analysis and compare results with existing literature | F | 2025-03-06 | 7 | bar: 2025-03-06 to 2025-03-12
Final model refinements | M | 2025-03-13 | 9 | bar: 2025-03-13 to 2025-03-21
Prepare final report | S | 2025-03-22 | 14 | bar: 2025-03-22 to 2025-04-04
Final report submission | S | 2025-04-04 | 1 | 2025-04-04: #VALUE!
Prepare final presentation | S | 2025-03-31 | 7 | bar: 2025-03-31 to 2025-04-06
Final Presentation | S | 2025-04-07 | 1 | 2025-04-07: #VALUE!